## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 144
|  | Days In Sprint: |  |  |  | 20
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
View breaking news | 36 | Days (Points Completed) 1: 6; Days (Points Completed) 2: 9; Days (Points Completed) 3: 9; Days (Points Completed) 4: 5; Days (Points Completed) 5: 4 | 3 | 91.67%
View weather forecasting | 36 | Days (Points Completed) 6: 9; Days (Points Completed) 7: 10; Days (Points Completed) 8: 9; Days (Points Completed) 9: 4; Days (Points Completed) 10: 3 | 1 | 97.22%
View the schedule of program | 36 | Days (Points Completed) 11: 9; Days (Points Completed) 12: 11; Days (Points Completed) 13: 9; Days (Points Completed) 14: 5; Days (Points Completed) 15: 2 | 0 | 100%
able to plae a query | 36 | Days (Points Completed) 16: 12; Days (Points Completed) 17: 10; Days (Points Completed) 18: 7; Days (Points Completed) 19: 4; Days (Points Completed) 20: 1 | 2 | 94.44%
0 | bar: Days (Points Completed) 1; Days (Points Completed) 3; Days (Points Completed) 5; Days (Points Completed) 7; Days (Points Completed) 9; Days (Points Completed) 11; Days (Points Completed) 13; Days (Points Completed) 15; Days (Points Completed) 17; Days (Points Completed) 19
Effort Remaining | 144 | 138 | 129 | 120 | 115 | 111 | 102 | 92 | 83 | 79 | 76 | 67 | 56 | 47 | 42 | 40 | 28 | 18 | 11 | 7 | 6 | 6 | 95.83%
Ideal Trend | 144 | 136.8 | 129.6 | 122.4 | 115.2 | 108 | 100.8 | 93.6 | 86.4 | 79.2 | 72 | 64.8 | 57.6 | 50.4 | 43.2 | 36 | 28.8 | 21.6 | 14.4 | 7.2 | -