## Sheet1
GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1